## List and Detail Of the Contract
Running Contract at WCC/TKD
SL NO | NAME OF CONTRACT | PERIOD/TRIPS | FROM | TO | TOTAL AMOUNT | FIRM NAME AND ADDRESS | CONTACT DETAILS | REMARKS | BILL STATUS
1 | Contract Agreement No. 197-S/183/CAMC-RO/C&W/DLI/17/MC-IV dated 18 May 2018 for “CAMC of RO plant at different C&W depots (New Delhi, Anand Vihar, Tuglakabad & Ghaziabad) over Delhi division (for 02 years). | 02 Years | 2018-06-27 |  | Rs 2839006.00( Rupees Twenty Eight Lakh Thirty Nine Thousand Six only) | M/S ICON RO Systems 3/102-A, Lalita Park, Vikas Marg, Laxmi Nagar, Delhi-92 | Mr Sharma Mob: 09810650775 / 9310093700 | Visit Completed till Mar 2020, Contract Extended till Sep 2020 | Bill Under process for the quarter Apr 2020 to Jun 2020. MB not received from division
2 | Contract Agreement No. 197-S-176-CAMC-Wheel lathe/01279570005082 dated 16/08/19 Tender for" Comprehensive Annual Maintenance Contract of Surface Wheel Lathe (Make-HYT) of wagon care centre, Tuglakabaad. (for 02 Years) | 02 Year | 2019-09-27 |  | Rs 2774419.00 (Rupees Twenty Four Lakh Thirt One Thousand Six Hundred Eighty Three and Eight Nine Paise) | M/S SBS Mechanical & Electrical Engineering Works, | Mr Bhattachaarya Mob: 09832342789 sbsmechanical@rediffmail.com | Visit for Ist, IInd and IIIrd quarter completed . SR DME/FR has ordered verbally to initiate the process for terminate ongoing CAMC view new lathe installed. | Bill not raised by the firm till to date. (Agreement made at division but not received at depot)
3 | Contract Agreement No. 197-S46/TRS-Wheel/DLI/19/00918770004163 dated 23 Sep 2019 regarding Transportation of Wheels through road truck to and fro between C&W depot over Delhi division and Jagadhari workshop. (for 02 years) | 2019-09-21 | 2021-10-04 | Per Wheel/Per Km rates | Total division contract rate Rs 3,31,40,380.36 (Rupees Three Crore Thirty One Lakhs Forty Thousand Three Hundred Eighty and Three Six Paisa only) | M/S GLOBE ECOLOGISTICS PVT LTD-AHMEDABAD 62 New York Tower A, Nr Thaltej Circle, Ahmedabad Gujarat India 380054 | Mr Rohit Kochhar - Mob : 9999375002,9999774002 | Vehicles are provided w.e.f 04/10/2019 | Bill fwd to division till Feb 2020, Bill ready till May 2020, MB not received from Division.
4 | Contract Agreement No. 197-S-60-HK-TKD-2017-19-MC-IV dated 17 Nov 2017 regarding mechanized cleaning of floor, pits & toilets, desilting of man holes, drains, disposal of industrial waste, scrap loading, horticultural, shed & office housekeeping at Wagon Care Centre, Tughlakabad. (for 02 years) | 02 Year | 2017-11-24 | 23-11-2019 25% extended | Rs 6046207.16 (Rupees Sixty Lakh Forty Six Thousand Two Hundred Seven ) | M/S National Enterprises 496, GH-9, Paschim Vihaar New Delhi -89 | Mr K Kumar Mob : 09250466659 | Contract commenced on 24/11/2017, Bills till Feb 2019 forwarded to DRM office for payment. 25% extended. IInd extension also done till Nov 2020 | Bill forwarded till Jun 2020 .
5 | LOA vide DME/Chg/NDLS letter No. 197-S/190/Prov. Of weld. activity/F.Depot/DLI/18/MC-IV dated 27/05/2019 Tender for “Provision of Round the clock Welding activities in Freight depots over Delhi Division for Two Years” | 02 Year | 2019-06-21 |  | Rs 21547257.60 (Rupees Two Crore Fifteen Lakh Forty Seven Thousand Two Hundred Fifty Seven and Sixty Paise only) | M/S Singh Enterprises Near JJ Nursing Home GT Road, Alinagar, Mughalsarai Chandauli - 232101 | Mr Rajesh Gupta 7985037899 Mr Sanjeev Singh 6203048593 | Work Started w.e.f 21/06/2019 ,Agreement received | Bill completed till Sep 19. Bill for Oct, Nov, Dec -19 and Jan 2020 are under process at depot level
6 | LOA vide DME/Chg/NDLS letter No. 197-S/223/Conversion of BLC wagon/TKD/19/MC-IV dated 09/09/2019 Tender for “Conversion of BLC rakes to 22 T axle load - BLCAM/BLCBM wagons as per drawing during ROH activity at wagon care centre, Tuglakabad for Two Years” | 02 Year | 2020-09-26 |  | Rs 2042163.90 (Rupees Twenty lakh Forty Two Thousand One Hundred Sixty Three and Ninety Paise only) | M/S Global Enterprises, 442, Subhash Puri, Kanpur Khera, Meerut, UP - 250001 | Mr Ishwinder Singh 9837383889 | Job Started from Dec 2019, material is to be provided by Railway | Bill completed till May -2020, pending view ADME signature
7 | LOA vide SRDME/FR/NDLS Letter DELHI DIVISION - MECHANICAL / 197- S/86/ATL / 01224030013552 for "repair of Automatic Twist Locks at Wagon Care Centre Tuglakabad for two years" | 2 Year |  |  | Rs 2223859.80 (Rupees Twenty Two lakh Twenty Three Thousand Eight Hundred Fifty Nine and Eighty Paise only) | M/S SHREE JAINA SOURCING AND CO- DELHI R 47/D, Dilshad Garden, Delhi - 110095 | Mr Rajiv Jain 9818298180 01122588115 01143029676 | Work was started on 19-20 Mar-20, thereafter lockdown, work resumed on 18 May 20, Work start date intimated to Division.
8 | LOA vide SRDME/FR/NDLS Letter DELHI DIVISION - MECHANICAL / 197- S-226 Retrofitment of ATL / 01224030013704 for "retrofitment of Automatic Twist Locks (ATL) in BFKHN wagons as per drawing at Wagon Care Centre Tuglakabad for 75 wagons" | 75 wagons (06 Month) |  |  | Rs 2079962.40 (Rupees Twenty lakh Seventy Nine Thousand Nine Hundred Sixty Two and Forty Paise only) | M/S SHREE JAINA SOURCING AND CO- DELHI R 47/D, Dilshad Garden, Delhi - 110095 | Mr Rajiv Jain 9818298180 01122588115 01143029676 | Not started view Material is yet to be provided by railway
9 | LOA vide SRDME/FR/NDLS letter No. DELHI DIVISION - MECHANICAL / 197- S181-Hiring of Truck/01362910013551 dated 13/01/2020 for "Hiring of full body truck (Carrying capacity-9 Ton) at wagon care centre Tuglakabad for transportation of Railway material between depots over Delhi division and JUDW " for 02 years. | 2 Year | 2020-02-29 |  | Rs 2597872.04 (Rupees Twenty Five lakh Ninety Seven Thousand Eight Hundred Seventy Two and Four Paise only) | M/s R K ROADLINES- GHAZIABAD - J 140 A SECTOR 9 VIJAY NAGAR , GHAZIABAD 201009 | Ravinder Gupta- 9868519332, Driver Pradeep Kumar - 9794104887 | Truck has not taken permission for no-entry timing zone yet, Sr DME/Fr/NDLS provisionally allowed for two month. Work started letter forwarded to division with no entry permission
10 | LOA vide SRDME/FR/NDLS letter No. DELHI DIVISION - MECHANICAL / 197- S175-Hiring - Vehicle/1379020013906 dated 18/01/2020 for "Hiring of Multi-utility Vehicle i.e.TATA XENON/ISUZU D-max or equivalent/ Higher version at Wagon Care Centre, Tuglakabad for Two years. | 2 Year | 2020-03-13 |  | Rs 1818298.86 (Rupees Eighteen lakh Eighteen Thousand Two Hundred Ninety Eight and Eight Six Paise only) | M/s ARAMISH INDIA PRIVATE LIMITED- NEW DELHI, PLOT NO. 185 FIE. PATPARGANJ INDUSTRIAL AREA, NEW DELHI 110092 | Mr Amit Rai 9818525122 | Work started already intimated to division,
11 | LOA vide SRDME/FR/NDLS letter No. DELHI DIVISION - MECHANICAL / 197- S187 CAMC of OH Cra/00919360014303 dated 24/01/2020 for " Comprehensive Annual Maintenance Contract for Over Head Cranes at Wagon Care Centre, Tughlakabad. | 2 Year |  |  | Rs 4041924.05 (Rupees Forty lakh Fourty One Thousand Nine Hundred Twenty Four and Zero Five Paise only) | M/s JAY TECHNICAL SERVICES - KOLKATA, 26/1/1B STRAND ROAD 4TH FLOOR ROOM NO.4 KOLKATA -700001, WEST BENGAL INDIA | Mr Ambrish Sharma/Mrs Namrata Sharma 9831092663 7044054673 9331764958 | Firm has submitted document for deputed employee and supervisor on 02 Mar 2020 and also Railway has proposed scheduled maintenance dates
12 | Letter No: DELHI DIVISION-MECHANICAL / 197-S216RefurbishofC / 01230030018838 Dated: 08/05/2020 for Refurbishment of old Cartridge Taper Roller Bearings class-E (Make : TIMKEN) from OEM (Refurbish & return) for Wagon Care Centre, Tughlakabad for Two years.
Completed (not to be mentioned)
8 | Contract Agreement No. 197-S/86/ATL-Rep/TKD/17/MC-IV dated 14 Jul 2017 Tender for " Repair of Automatic Twist Lock at Wagon Care Centre, Tuglakabaad over Delhi division (for 01 year) | 01 Year | 2017-08-01 | 2018-08-01 | Rs 4905588.00 (Rupees Forty Nine Lakh Five Thousand Five Hundred Eighty Eight only) | M/S Sanrok Enterprises FF-11 Sco-35 Distt: Shopping Centre Sec-16 Faridabad, Haryana | Mr Trilok Singh Rawat 9818661413 | Completed IN APR 2019 Commnenced w.e.f 26/08/2017 | NO BILL DUE
9 | Contract Agreement No. 197-S/181/Hiring of Truck/CC.9T/TKD/16/MC-IV dated 06/06/2017 "Hiring of full body truck (Cap.-9 Ton) at wagon care centre Tuglakabad for transportation of railway material between depots over Delhi division and JUDW for " at Wagon care centre ,Tuglakabaad". (for 02 years) | 02 Years | 2017-06-01 | 2019-06-01 | Rs 1875464.00 (Rupees Eighteen Lakh Seventy Five Thousand Four Hundred Sixty Four) | M/S Shubham Enterprises, M-177, Sector-12, Pratap Vihar, Ghaziabad | Ravinder Gupta- 9868519332, Driver Pramod Kumar - 8447495250, UP81-BT-1806/TATA-1109 | COMPLETED NEW TENDER FLOATED, ONCE DISCHARED, AGAIN IN PROCESS | NO BILL DUE
10 | Contract Agreement No. 197-S-190/O.T.repair/Yard/TKD/16/MC-IV dated 07 Dec 2017 regarding " on train repair of BCACM/BCACBM and other wagons at Wagon Care Centre, Tughlakabad over Delhi Division for one year. (for 01 year) | 01 year | 2017-12-01 | 2018-12-01 | 1820050.00 (Rupees Eighteen lakh Twenty Thousand Fifty Only) | M/S Emergus India Advisors Pvt. Ltd. 402, 4th floor , Nirmal Tower, Barakhamba Road, New Delhi | Keshav- 9650560521, Owner Atul Mishra-9871762515 | Completed IN APR 2019 Commenced on 23/12/2017, | NO BILL DUE
11 | Contract Agreement No. 197-S/AMC-Computer/C&W/DLI/17/MC-IV dated 20 Feb 2018 regarding , Annual maintenance contract for computer and peripheral of at C&W Mechanical wing of Delhi Division.(01 year) | 01 year | 2018-02-01 |  | 999049.00 (Nine Lakh Ninety Thousand Forty Nine only) | M/s Pandit Ji computer Shop no. 04, Opp: Patliputra Nursing Home, Main Market Samaypur Delhi -42 | Mr Sanjay 8368174559 | Completed IN APR 2019 | operated from Division only
Note on B4: ALL RO INCLUDED IN THIS, ONLY TRAIN DUTY RO WAS INCLUDED FROM 2ND QUARTER ONWARDS SINCE ITS PREVIOUS WORK ORDER WAS COMPLETED LATE.
Note on C6: Author: As per LOA it was for 2 years . But as per agreement it is for 01 year, Again correction of agreement came in which it was for two years.
Note on B15: Not started till to date
Note on B23: Contract DP extended till Dec 18
Note on B25: contract will be completing on Dec 2018

## menpower status
| Contract Description | MenPower Status | Remarks
1 | “CAMC of RO plant at different C&W depots (New Delhi, Anand Vihar, Tuglakabad & Ghaziabad) over Delhi division (for 02 years). | Technician from the firm visit quarterly or on complain | Manpower not specified in the contract
2 | Comprehensive Annual Maintenance Contract of Surface Wheel Lathe (Make-HYT) of wagon care centre, Tuglakabaad. (for 02 Years) | Service Engineers along with Technician from the firm visit quarterly or on complain | Manpower not specified in the contract
3 | Transportation of Wheels through road truck to and fro between C&W depot over Delhi division and Jagadhari workshop. (for 02 years) | Driver along with suitable vehicle from the firm visit WCC/TKD as per wheel demand through C&W control | Manpower not specified in the contract
4 | mechanized cleaning of floor, pits & toilets, desilting of man holes, drains, disposal of industrial waste, scrap loading, horticultural, shed & office housekeeping at Wagon Care Centre, Tughlakabad. (for 02 years) | 13 Nos
5 | “Provision of Round the clock Welding activities in Freight depots over Delhi Division for Two Years” | 16 Welder and 16 helper | out of this quantity 03 welder 03 helper sent to GZB depot
6 | “Conversion of BLC rakes to 22 T axle load - BLCAM/BLCBM wagons as per drawing during ROH activity at wagon care centre, Tuglakabad for Two Years” | Personnels from the firm are deputed as and when Bogies are available to modify. | Manpower not specified in the contract
7 | "Repair of Automatic Twist Locks at Wagon Care Centre Tuglakabad for two years" | Personnels from the firm are deputed as and when repair of ATL arises . | Manpower not specified in the contract
8 | "Retrofitment of Automatic Twist Locks (ATL) in BFKHN wagons as per drawing at Wagon Care Centre Tuglakabad for 75 wagons" |  | Not Started
9 | "Hiring of full body truck (Carrying capacity-9 Ton) at wagon care centre Tuglakabad for transportation of Railway material between depots over Delhi division and JUDW " for 02 years. | Driver along with truck deputed permanently at WCC/TKD | Only Driver and cleaner mentioned
10 | "Hiring of Multi-utility Vehicle i.e.TATA XENON/ISUZU D-max or equivalent/ Higher version at Wagon Care Centre, Tuglakabad for Two years. | Driver along with vehicle permanently at WCC/TKD | Only Driver mentioned
11 | " Comprehensive Annual Maintenance Contract for Over Head Cranes at Wagon Care Centre, Tughlakabad. | Service Engineers along with Technician from the firm visit quarterly or on complain | Manpower not specified in the contract

## Bill Status
Status Contract at WCC/TKD
SL NO | NAME OF CONTRACT | PERIOD/TRIPS | FIRM NAME AND ADDRESS | BILL TYPE | BILL STATUS | AMOUNT PAID | PENALTY | EXCESS BILL
1 | Contract Agreement No. 197-S/183/CAMC-RO/C&W/DLI/17/MC-IV dated 18 May 2018 for “CAMC of RO plant at different C&W depots (New Delhi, Anand Vihar, Tuglakabad & Ghaziabad) over Delhi division (for 02 years). | 02 Years From 27-06-2018 (Extended till 26-09-2020) | M/S ICON RO Systems 3/102-A, Lalita Park, Vikas Marg, Laxmi Nagar, Delhi-92 | Quarterly Bill | Bill completed till Mar 2020.( Bill for 8th quarter Apr-May-Jun 2020 is under process)MB is with Division
2 | Contract Agreement No. 197-S-176-CAMC-Wheel lathe/01279570005082 dated 16/08/19 Tender for" Comprehensive Annual Maintenance Contract of Surface Wheel Lathe (Make-HYT) of wagon care centre, Tuglakabaad. (for 02 Years) | 02 Year From 27-09-2019 (Discontinuationrequest fwd to SRDME/FR ) | M/S SBS Mechanical & Electrical Engineering Works, | Quarterly Bill | 03 quarter bill pending .Bill by the firm would be raised once agreement is done.
3 | Contract Agreement No. 197-S46/TRS-Wheel/DLI/19/00918770004163 dated 23 Sep 2019 regarding Transportation of Wheels through road truck to and fro between C&W depot over Delhi division and Jagadhari workshop. (for 02 years) | From 21-09-2019 Till 04-10-2021 | M/S GLOBE ECOLOGISTICS PVT LTD-AHMEDABAD 62 New York Tower A, Nr Thaltej Circle, Ahmedabad Gujarat India 380054 | Quarterly Bill | Bill fwd to division till Feb 2020. ( Bill for Mar-Apr-May-Jun-Jul Completed at depot level)MB is with division
4 | Contract Agreement No. 197-S-60-HK-TKD-2017-19-MC-IV dated 17 Nov 2017 regarding mechanized cleaning of floor, pits & toilets, desilting of man holes, drains, disposal of industrial waste, scrap loading, horticultural, shed & office housekeeping at Wagon Care Centre, Tughlakabad. (for 02 years) | 02 Year From 24-11-2017 | M/S National Enterprises 496, GH-9, Paschim Vihaar New Delhi -89 | Monthly Bill | Bill completed till Jun 20 .MB is with Division
5 | LOA vide DME/Chg/NDLS letter No. 197-S/190/Prov. Of weld. activity/F.Depot/DLI/18/MC-IV dated 27/05/2019 Tender for “Provision of Round the clock Welding activities in Freight depots over Delhi Division for Two Years” | 02 Year From 21-06-2019 | M/S Singh Enterprises Near JJ Nursing Home GT Road, Alinagar, Mughalsarai Chandauli - 232101 | Monthly Bill . | Bill completed till Jan 20 . (Bill also under process till May 2020 at Depot level)
6 | LOA vide DME/Chg/NDLS letter No. 197-S/223/Conversion of BLC wagon/TKD/19/MC-IV dated 09/09/2019 Tender for “Conversion of BLC rakes to 22 T axle load - BLCAM/BLCBM wagons as per drawing during ROH activity at wagon care centre, Tuglakabad for Two Years” | 02 Year From 26-09-2020 | M/S Global Enterprises, 442, Subhash Puri, Kanpur Khera, Meerut, UP - 250001 | Monthly Bill . | Bill completed till Jun - 20. MB is with Division
7 | LOA vide SRDME/FR/NDLS Letter DELHI DIVISION - MECHANICAL / 197- S/86/ATL / 01224030013552 for "repair of Automatic Twist Locks at Wagon Care Centre Tuglakabad for two years" | 2 Year From Mar 2020 | M/S SHREE JAINA SOURCING AND CO- DELHI R 47/D, Dilshad Garden, Delhi - 110095 | Monthly Bill . | Waiting for agreement
8 | LOA vide SRDME/FR/NDLS Letter DELHI DIVISION - MECHANICAL / 197- S-226 Retrofitment of ATL / 01224030013704 for "retrofitment of Automatic Twist Locks (ATL) in BFKHN wagons as per drawing at Wagon Care Centre Tuglakabad for 75 wagons" | 75 wagons (06 Month) , Yet to Start | M/S SHREE JAINA SOURCING AND CO- DELHI R 47/D, Dilshad Garden, Delhi - 110095 | Monthly Bill . | Waiting for agreement
9 | LOA vide SRDME/FR/NDLS letter No. DELHI DIVISION - MECHANICAL / 197- S181-Hiring of Truck/01362910013551 dated 13/01/2020 for "Hiring of full body truck (Carrying capacity-9 Ton) at wagon care centre Tuglakabad for transportation of Railway material between depots over Delhi division and JUDW " for 02 years. | 2 Year From 29 Feb 202 | M/s R K ROADLINES- GHAZIABAD - J 140 A SECTOR 9 VIJAY NAGAR , GHAZIABAD 201009 | Monthly Bill . | Bil completed till Aug 2020 .
10 | LOA vide SRDME/FR/NDLS letter No. DELHI DIVISION - MECHANICAL / 197- S175-Hiring - Vehicle/1379020013906 dated 18/01/2020 for "Hiring of Multi-utility Vehicle i.e.TATA XENON/ISUZU D-max or equivalent/ Higher version at Wagon Care Centre, Tuglakabad for Two years. | 2 Year From 14 Mar 2020 | M/s ARAMISH INDIA PRIVATE LIMITED- NEW DELHI, PLOT NO. 185 FIE. PATPARGANJ INDUSTRIAL AREA, NEW DELHI 110092 | Monthly Bill . | Bil completed till Jun 2020 . For Jul & Aug 2020 bill completd at depot level. MB is with Division
11 | LOA vide SRDME/FR/NDLS letter No. DELHI DIVISION - MECHANICAL / 197- S187 CAMC of OH Cra/00919360014303 dated 24/01/2020 for " Comprehensive Annual Maintenance Contract for Over Head Cranes at Wagon Care Centre, Tughlakabad. | 2 Year From 24 May 2020 | M/s JAY TECHNICAL SERVICES - KOLKATA, 26/1/1B STRAND ROAD 4TH FLOOR ROOM NO.4 KOLKATA -700001, WEST BENGAL INDIA | Quarterly Bill | Waiting for Agreement
6
Completed (not to be mentioned)
8 | Contract Agreement No. 197-S/86/ATL-Rep/TKD/17/MC-IV dated 14 Jul 2017 Tender for " Repair of Automatic Twist Lock at Wagon Care Centre, Tuglakabaad over Delhi division (for 01 year) | 01 Year | M/S Sanrok Enterprises FF-11 Sco-35 Distt: Shopping Centre Sec-16 Faridabad, Haryana | NO BILL DUE
9 | Contract Agreement No. 197-S/181/Hiring of Truck/CC.9T/TKD/16/MC-IV dated 06/06/2017 "Hiring of full body truck (Cap.-9 Ton) at wagon care centre Tuglakabad for transportation of railway material between depots over Delhi division and JUDW for " at Wagon care centre ,Tuglakabaad". (for 02 years) | 02 Years | M/S Shubham Enterprises, M-177, Sector-12, Pratap Vihar, Ghaziabad | NO BILL DUE
10 | Contract Agreement No. 197-S-190/O.T.repair/Yard/TKD/16/MC-IV dated 07 Dec 2017 regarding " on train repair of BCACM/BCACBM and other wagons at Wagon Care Centre, Tughlakabad over Delhi Division for one year. (for 01 year) | 01 year | M/S Emergus India Advisors Pvt. Ltd. 402, 4th floor , Nirmal Tower, Barakhamba Road, New Delhi | NO BILL DUE
11 | Contract Agreement No. 197-S/AMC-Computer/C&W/DLI/17/MC-IV dated 20 Feb 2018 regarding , Annual maintenance contract for computer and peripheral of at C&W Mechanical wing of Delhi Division.(01 year) | 01 year | M/s Pandit Ji computer Shop no. 04, Opp: Patliputra Nursing Home, Main Market Samaypur Delhi -42 | operated from Division only
Note on B4: ALL RO INCLUDED IN THIS, ONLY TRAIN DUTY RO WAS INCLUDED FROM 2ND QUARTER ONWARDS SINCE ITS PREVIOUS WORK ORDER WAS COMPLETED LATE.
Note on B16: Author: tender opening date is 27/03/2017 but LOA sent date is 13/06/2017
Note on B23: Contract DP extended till Dec 18
Note on B25: contract will be completing on Dec 2018

## Expenditure against Labour
[7 empty] | Department : | Mechanical/C&W/DLI/TKD
FY: 2017-2018
Department which execute the tripartite agreement on Zones/Division | List of activities for which engaged | Monthwise number of contractual worker engaged |  | Avg. men / day | Monthwise amount of payment made to contractual worker | list of activities discontinued | Monthwise reduction in number of contractual workers | Competent authority to approve award of the contracts on Zones/Divisions | Remarks
Mechanical | On train repair of BCACM/BCACBM and other wagons. | 2017-12-01 | 34 | 1.0968 | 25405 |  |  | SRDME/FR
|  | 2018-01-01 | 138 | 4.4516 | 103270
|  | 2018-02-01 | 120 | 4.2857 | 89800
|  | 2018-03-01 | 105 | 3.3871 | 78575
Mechanical | mechanized cleaning of floor, pits | 2017-03-01 | 370 | 12 | 138380 |  |  | SRDME/FR
| & toilets, desilting of man holes, drains, | 2017-04-01 | 384 | 13 | 196992
| disposal of industrial waste, scrap | 2017-05-01 | 367 | 12 | 188271
| loading, horticultural, | 2017-06-01 | 357 | 12 | 183141
| shed & office housekeeping | 2017-07-01 | 362 | 12 | 185706
|  | 2017-08-01 | 400 | 13 | 205200
|  | 2017-09-01 | 150 | 5 | 74385
|  | 2017-10-01 | 155 | 5 | 76950
|  | 2017-11-01 | 150 | 5 | 74385
|  | 2017-12-01 | 362 | 12 | 185706
|  | 2018-01-01 | 399 | 13 | 204687
|  | 2018-02-01 | 323 | 12 | 165699
|  | 2018-03-01 | 378 | 12 | 193914
[7 empty] | Department : | Mechanical/C&W/DLI
FY: 2018-2019
Department which execute the tripartite agreement on Zones/Division | List of activities for which engaged | Monthwise number of contractual worker engaged |  | Avg. men / day | Monthwise amount of payment made to contractual worker | list of activities discontinued | Monthwise reduction in number od contractual workers | Competent authority to approve award of the contracts on Zones/Divisions | Remarks
Mechanical | On train repair of BCACM/BCACBM and other wagons. | 2018-04-01 | 114 | 3.8 | 86000 |  |  | SRDME/FR
|  | 2018-05-01 | 125 | 4.0323 | 93120
|  | 2018-06-01 | 122 | 4.0667 | 91565
|  | 2018-07-01 | 139 | 4.4839 | 104210
|  | 2018-08-01 | 100 | 3.2258 | 73990
|  | 2018-09-01 | 119 | 3.9667 | 88515
|  | 2018-10-01 | 96 | 3.2 | 72070
|  | 2018-11-01 | 100 | 3.3333 | 74680
|  | 2018-12-01 | 118 | 3.8065 | 87690
|  | 2019-01-01 | 115 | 3.7097 | 86135
|  | 2019-02-01 | 117 | 4.1786 | 87785
|  | 2019-03-01 | 125 | 4.0323 | 93005
Mechanical | mechanized cleaning of floor, pits
| & toilets, desilting of man holes, drains, | 2018-04-01 | 354 | 12 | 189036 |  |  | SRDME/FR
| disposal of industrial waste, scrap | 2018-05-01 | 391 | 13 | 208794
| loading, horticultural, | 2018-06-01 | 375 | 13 | 200250
| shed & office housekeeping | 2018-07-01 | 401 | 13 | 214134
|  | 2018-08-01 | 380 | 12 | 202920
|  | 2018-09-01 | 341 | 11 | 182094
|  | 2018-10-01 | 341 | 11 | 182094
|  | 2018-11-01 | 317 | 11 | 169278
|  | 2018-12-01 | 351 | 11 | 187434
|  | 2019-01-01 | 327 | 11 | 174618
|  | 2019-02-01 | 268 | 10 | 143112
|  | 2019-03-01 | 314 | 10 | 167676
[7 empty] | Department : | Mechanical/C&W/DLI/TKD
FY: 2019-2020
Department which execute the tripartite agreement on Zones/Division | List of activities for which engaged | Monthwise number of contractual worker engaged |  | Avg. men / day | Monthwise amount of payment made to contractual worker | list of activities discontinued | Monthwise reduction in number od contractual workers | Competent authority to approve award of the contracts on Zones/Divisions | Remarks
Mechanical | On train repair of BCACM/BCACBM and other wagons. | 2019-04-01 | 15 | 30 | 120300 |  |  | SRDME/FR
|  | 2019-05-01 | nil | 0 | nil | Discontinued
Mechanical | Provision of Round the clock Welding activities in Freight depots over Delhi Division for Two Years | 2019-06-01 | 262 | 8.7333 | 223734 |  |  | SRDME/FR
|  | 2019-07-01 | 840 | 27.0968 | 724067
|  | 2019-08-01 | 972 | 31.3548 | 834107
|  | 2019-09-01 | 936 | 31.2 | 801381
|  | 2019-10-01 | 906 | 30.2 | 778164
|  | 2019-11-01 | 878 | 29.2667 | 752132
|  | 2019-12-01 | 952 | 30.7097 | 816112
|  | 2020-01-01 | 940 | 30.3226 | 806826
|  | 2020-02-01 | 743 | 25.6207 | 637421
|  | 2020-03-01 | 858 | 27.6774 | 733466
Mechanical | mechanized cleaning of floor, pits
| & toilets, desilting of man holes, drains, | 2019-04-01 | 347 | 12 | 198137 |  |  | SRDME/FR
| disposal of industrial waste, scrap | 2019-05-01 | 322 | 10 | 183862
| loading, horticultural, | 2019-06-01 | 288 | 10 | 164448
| shed & office housekeeping | 2019-07-01 | 350 | 11 | 199850
|  | 2019-08-01 | 375 | 12 | 214125
|  | 2019-09-01 | 343 | 11 | 195853
|  | 2019-10-01 | 268 | 9 | 153028
|  | 2019-11-01 | 276 | 9 | 157596
|  | 2019-12-01 | 293 | 9 | 167303
|  | 2020-01-01 | 264 | 9 | 150744
|  | 2020-02-01 | 265 | 9 | 151315
|  | 2020-03-01 | 270 | 9 | 154170

## Yearwise Contract Expenditure
Expenditure of Contract Jul-2017 to Mar-2018 AT WCC TKD (In Rs)
[55 empty] | 2017 |  |  |  |  | 2018
SL NO | NAME OF CONTRACT | [51 empty] | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | [24 empty] | Mar | Total
1 | Transportation of Wheels | [51 empty] | 576784 | 714425 | 745224 | 686969 | 627874 | 856864 | 731289 | 938119 | [24 empty] | 895649 | 6773197
2 | Housekeeping | [51 empty] | 140121 | 117247 | 65730 | 65730 | 77540 | 252708 | 232943 | 220867 | [24 empty] | 232943 | 1405829
3 | Hiring of full Body Truck | [51 empty] | 78144 | 78144 | 78144 | 78144 | 78144 | 78144 | 78144 | 78144 | [24 empty] | 78144 | 703296
4 | Hiring of Multiutility vehicle (Bolero) | [51 empty] | 40082 | 40082 | 40082 | 40082 | 40082 | 40082 | 40082 | 40082 | [24 empty] | 40082 | 360738
5 | Repair of Automatic twist lock at ICD | [51 empty] | 0 | 340954 | 866031 | 120157 | 429757 | 36554 | 421894 | 431033 | [24 empty] | 380119 | 3026499
6 | On train repair BCACM/BCACBM (welding) | [51 empty] | 0 | 0 | 0 | 0 | 0 | 37405 | 151270 | 137800 | [24 empty] | 150575 | 477050
7 | CAMC of wheel lathe | [51 empty] | 117117 | 117117 | 117117 | 117117 | 117117 | 117117 | 117117 | 117117 | [24 empty] | 117117 | 1054053
8 | CAMC of Overhead crane | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [24 empty] | 0 | 0
9 | CAMC of RO plant | [51 empty] | 2708 | 2708 | 2708 | 2708 | 2708 | 2708 | 2708 | 2708 | [24 empty] | 2708 | 24372
10 | CAMC of computer and peripherals | [51 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [24 empty] | 0 | 0
[53 empty] | 2018 Feb: Total | [25 empty] | 13825034
Expenditure of Contract
[6 empty] | 2014 | [11 empty] | 2015 | [11 empty] | 2016 | [13 empty] | 2017 | [8 empty] | 2017 Sep: 2018 | [5 empty] | 2019 | [10 empty] | 2020
SL NO | NAME OF CONTRACT | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
1 | Transportation of Wheels |  |  |  | 118720 | 97934 | 140103 | 18574 | 187463 | 242037 | 57507 | 229846 | 222846 | 103316 | 51551 | 80485 | 164485 | 142294 | 138463 | 188250 | 84572 | 175336 | 559627 | 533659 | 621244 | 700055 | 869914 | 757151 | 760198 | 867667 | 378525 | 603955 | 855393 | 1100532 | 864775 | 683979 | 678214 | 778632 | 546520 | 799869 | 707470 | 812740 | 612944 | 545983 | 714425 | 727008 | 686969 | 627874 | 856864 | 731289 | 938119 | 900849 | 797770 | 997213 | 1004599 | 694355 | 827317 | 819930 | 997213 | 686969 | 782996 | 635261 | 657422 | 723902 | 531847 | 650035 | 641708 | 626464 | 443205 | 258066 | 377848 | 346843 | 138178 | 328935 | 473212 | 0 | 664567 | 480501 | 640437.22 | 717788.73
2 | Repair of Automatic twist lock at ICD | 2016 May: 236447.9; 2016 Jun: 910582.7; 2016 Jul: 226936; 2016 Aug: 838561; 2016 Sep: 523236; 2016 Oct: 868457; 2016 Nov: 812742; 2016 Dec: 491982; 2016 Jan: 182092; 2016 Feb: 66586; 2016 Mar: 10871; 2016 Apr: 20383; 2016 May: 0; 2016 Jun: 0; 2017 Jul: 0; 2017 Aug: 340954; 2017 Sep: 800708; 2017 Oct: 101828; 2017 Nov: 429727; 2017 Dec: 26554; 2017 Jan: 421894; 2017 Feb: 431033; 2017 Mar: 380119; 2017 Apr: 49609; 2017 May: 86162; 2018 Jun: 369675; 2018 Jul: 461059; 2018 Aug: 450615; 2018 Sep: 374897; 2018 Oct: 75718; 2018 Nov: 90079; 2018 Dec: 199851; 2018 Jan: 787709; 2018 Feb: 92690; 2018 Mar: 120105; 2018 Apr: 24804; 2019 May: 0; 2019 Jun: 0; 2019 Jul: 0; 2019 Aug: 0; 2019 Sep: 0; 2019 Oct: 0; 2019 Nov: 450000; 2019 Dec: 0; 2019 Jan: 0; 2019 Feb: 0; 2019 Mar: 0
3 | On train repair BCACM/BCACBM (welding) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122000 | 139565 | 146210 | 139990 | 136941 | 136941 | 133270 | 123480 | 145265 | 137935 | 129385 | 146805 | 18030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Housekeeping |  |  |  | 103129 | 79389 | 91105 | 91719 | 97816 | 88580 | 97807 | 92776 | 99570 | 99477 | 81671 | 88721 | 77225 | 79824 | 78143 | 84823 | 64696 | 113529 | 100718 | 135254 | 139305 | 107347 | 100610 | 92473 | 52883 | 129870 | 104465 | 91543 | 111652 | 93321 | 110955 | 111441 | 66248 | 69299 | 90244 | 138461 | 154089 | 139647 | 130162 | 139851 | 82113 | 197191 | 0 | 38858 | 245811 | 226643 | 203385 | 225104 | 211944 | 214902 | 187272 | 226771 | 195258 | 170143 | 192197 | 184114 | 174202 | 206661 | 174271 | 221967 | 179679 | 206191 | 206797 | 190901 | 179295 | 155276 | 177186 | 176388 | 194184 | 188674 | 159303 | 199185 | 183091 | 168969 | 164411
5 | Hiring of Multiutility vehicle | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40082 | 40082 | 40082 | 40082 | 40082 | 40082 | 40082 | 40082 | 40082 | 40082 | 40082 | 40082 | 40082 | 40082 | 40082 | 40082 | 40082 | 40082 | 40082 | 40082 | 40082 | 40082 | 40082 | 40082 | 40082 | 40082 | 40082 | 40082 | 40082 | 40082 | 0 | 0 | 39881 | 64652 | 64652 | 64652 | 64652 | 64652
6 | Hiring of Full body Truck | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78144 | 78144 | 78144 | 78144 | 78144 | 78144 | 78144 | 78144 | 78144 | 78144 | 78144 | 78144 | 78144 | 78144 | 78144 | 78144 | 78144 | 78144 | 78144 | 78144 | 78144 | 78144 | 78144 | 78144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90966 | 91466 | 91466 | 91466 | 91466 | 91466
7 | CAMC of wheel lathe | 170833 | 170833 | 170833 | 170833 | 170833 | 170833 | 170833 | 170833 | 170833 | 170833 | 170833 | 170833 | 170833 | 170833 | 170833 | 170833 | 170833 | 170833 | 170833 | 170833 | 170833 | 170833 | 170833 | 170833 | 170833 | 170833 | 170833 | 170833 | 170833 | 170833 | 140504 | 140504 | 140504 | 170833 | 170833 | 170833 | 164000 | 164000 | 164000 | 164000 | 164000 | 164000 | 164000 | 164000 | 164000 | 164000 | 164000 | 164000 | 164000 | 164000 | 164000 | 101320 | 101320 | 101320 | 101320 | 101320 | 101320 | 101320 | 101320 | 101320 | 101320 | 101320 | 101320 | 101320 | 101320 | 101320 | 101320 | 101320 | 101320 | 107828 | 107828 | 107828 | 107828 | 107828 | 107828 | 107828 | 107828 | 107828
8 | CAMC of RO plant | 2708 | 2708 | 2708 | 2708 | 2708 | 2708 | 2708 | 2708 | 2708 | 2708 | 2708 | 2708 | 2708 | 2708 | 2708 | 2708 | 2708 | 2708 | 2708 | 2708 | 2708 | 2708 | 2708 | 2708 | 2708 | 2708 | 2708 | 2708 | 2708 | 2708 | 2708 | 2708 | 2708 | 2708 | 2708 | 2708 | 2708 | 2708 | 2708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4426 | 4426 | 4426 | 4426 | 4426 | 4426 | 4426 | 4426 | 4426 | 4426 | 4426 | 4426 | 4426 | 4426 | 4426 | 4426 | 4426 | 4426 | 4426 | 4426 | 4426 | 4426 | 4426 | 4426 | 4426 | 4426 | 4426
9 | CAMC of Overhead crane | 2017 Apr: 0; 2017 May: 0; 2018 Jun: 0; 2018 Jul: 0; 2018 Aug: 0; 2018 Sep: 0; 2018 Oct: 0; 2018 Nov: 0; 2018 Dec: 0; 2018 Jan: 0; 2018 Feb: 0; 2018 Mar: 0; 2018 Apr: 0; 2019 May: 0; 2019 Jun: 0; 2019 Jul: 0; 2019 Aug: 0; 2019 Sep: 0; 2019 Oct: 0; 2019 Nov: 0; 2019 Dec: 0; 2019 Jan: 0; 2019 Feb: 0
10 | TIMKEN CTRB OVERHAULING | 2017 Apr: 0; 2017 May: 0; 2018 Jun: 0; 2018 Jul: 0; 2018 Aug: 0; 2018 Sep: 0; 2018 Oct: 0; 2018 Nov: 0; 2018 Dec: 0; 2018 Jan: 0; 2018 Feb: 0; 2018 Mar: 0; 2018 Apr: 0; 2019 May: 0; 2019 Jun: 0; 2019 Jul: 0; 2019 Aug: 0; 2019 Sep: 0; 2019 Oct: 0; 2019 Nov: 0; 2019 Dec: 0; 2019 Jan: 0; 2019 Feb: 0; 2019 Mar: 0
11 | Provision of Welding activity round the clock | 2016 Jul: 8918259; 2016 Aug: 5168493.6; 2016 Sep: 1170382; 2016 Oct: 1938510; 2016 Nov: 32496; 2016 May: 8862534; 2016 Jun: 2953200; 2017 Jul: 1782854; 2017 Aug: 360738; 2017 Sep: 781440; 2017 Oct: 1968000; 2018 Sep: 0; 2018 Oct: 0; 2018 Nov: 0; 2018 Dec: 0; 2018 Jan: 0; 2018 Feb: 0; 2018 Mar: 0; 2018 Apr: 0; 2019 May: 0; 2019 Jun: 249033; 2019 Jul: 700358; 2019 Aug: 872710; 2019 Sep: 841133; 2019 Oct: 796540; 2019 Nov: 755128; 2019 Dec: 844887.89; 2019 Jan: 836001; 2019 Feb: 841133; 2019 Mar: 742272; 2020 Apr: 718720; 2020 May: 660925
12 | IMS certification | 2014 Aug: 1550382; 2014 Sep: 0; 2014 Oct: 1111760; 2014 Nov: 2049996; 2014 Dec: 32496; 2015 Aug: 4935050; 2015 Sep: 0; 2015 Oct: 1173947; 2015 Nov: 2049996; 2015 Dec: 32496; 2016 Jul: 16-17; 2016 Aug: 17228140.6; 2016 May: 17-18; 2017 Jul: 16708766; 2018 Sep: 0; 2018 Oct: 0; 2018 Nov: 0; 2018 Dec: 0; 2018 Jan: 0; 2018 Feb: 0; 2018 Mar: 0; 2018 Apr: 0; 2019 May: 0; 2019 Jun: 0; 2019 Jul: 0; 2019 Aug: 0; 2019 Sep: 0; 2019 Oct: 0; 2019 Nov: 0; 2019 Dec: 0; 2019 Jan: 0; 2019 Feb: 0; 2019 Mar: 0; 2020 Aug: 221005
13 | Bogie Modification | 2014 Jul: 14-15; 2014 Aug: 4744634; 2015 Aug: 15-16; 2015 Sep: 8191489; 2018 Sep: 0; 2018 Oct: 0; 2018 Nov: 0; 2018 Dec: 0; 2018 Jan: 0; 2018 Feb: 0; 2018 Mar: 0; 2018 Apr: 0; 2019 May: 0; 2019 Jun: 0; 2019 Jul: 0; 2019 Aug: 0; 2019 Sep: 0; 2019 Oct: 0; 2019 Nov: 0; 2019 Dec: 5941; 2019 Jan: 55951; 2019 Feb: 75263; 2019 Mar: 42611; 2020 Apr: 0; 2020 May: 0; 2020 Jun: 47271; 2020 Jul: 94165
14 | Fitment of ATL in retrofitment of BFKHN wagon
[54 empty] | 9624947 | 3158169 | 1637787 | 2359702 | 480984 | 937728 | 1215840 | 39834 |  |  |  | 4816341 | 474804 | 18030 | 2213059 | 400619 | 338720 | 1254888 | 53112 | 0 | 0 | 7479195.89 | 0 | 179766
[54 empty] | 18-19 |  | 19454991 | [11 empty] | 19-20 | 17228534.89
Note on BU23: Author: Work order was released for 300 nos ATL repair for month NOV DEC -2019 and JAN 2020..
Note on AU25: WCC: amount of contract is for 90 days
Note on AG33: Author: APR 16 TO MAR 17
Note on AQ33: Author: APR 17 TO MAR 18
Note on I34: Author: APR 14 TO MAR 15
Note on V34: Author: APR 15 TO MAR 16
Note on BC39: Author: APR 18 TO MAR 19
Note on BQ39: Author: APR 19 TO MAR 20

## TPT wheels
Contract Agreement No. LOA No. DELHI DIVISION –MECHANICAL/197-S46TRS-WheelDLI19 / 00918770004163 dated 30/07/2019 for “transportation
of wheel through road truck (CC-9MT) to and fro between C&W depot over Delhi division and Jagadhari workshop (for two year).
Total division contract rate Rs 3,31,40,380.36 (Rupees Three Crore Thirty One Lakhs Forty Thousand Three Hundred Eighty and Three Six Paisa only)
TKD - 1100 trip (TO & FRO EACH ) (Rs 8125440 TKD TO JUDW AND Rs 8125440 JUDW TO TKD )
M/s GLOBE ECOLOGISTICS PVT LTD. 62 New York Tower A Nr Thaltej Circle, Ahmedabad Gujarat, India - 380054
W.E.F : 04 Oct 2019
S. No | Bill No & Dt FOR THE MONTH | Bill raised by Firm (in Rs)(incl GST) | Penalty (in Rs) | GST @ 5% | Net verified Amount
|  | A | B | C
1 | Bill No DELKK-00000998 dtd. 11/01/2020, for Oct -19 | 426806 | 3800 | 20324.08 | 377848.3
2 | Bill No DELKK-00001219 dtd. 13/01/2020, for Nov -19 | 517382 | 145900 | 24637.23 | 346844.55
3 | Bill No DELKK-00001220 dtd. 15/01/2020, for Dec -19 | 465232 | 304900 | 22153.9 | 138177.99
4 | Bill No DELKK-00001284 dtd. 03/02/2020, for Jan -20 | 613447 | 255300 | 29211.7619 | 328935
5 | Bill No DELKK-00001386 dtd. 11/03/2020, for Feb -20 | 706768 | 199900 | 33655.619 | 473212
6 | Bill No DELKK-00000131 dtd. 08/06/2020, for Mar -20 | 542084 | 59000 | 25813.54 | 457271
7 | Bill No DELKK-00000148 dtd. 09/06/2020, for Apr -20 | 86262.97 | 0 | 4313.15 | 86263
8 | Bill No DELKK-00000152 dtd. 23/06/2020, for May -20 | 503200.67 | 22700 | 25160.03 | 480501
9 | Bill No DELKK-00000176 dtd. 23/07/2020, for Jun -20 | 672459 | 0 | 32021.86 | 640437.22
10 | Bill No DELKK-00000216 dtd. 12/08/2020, for Jul -20 | 753678 | 0 | 35889.44 | 717788.73
11
12
13
14

## ATL Repair in ICD
LOA vide SRDME/FR/NDLS Letter DELHI DIVISION - MECHANICAL / 197- S/86/ATL / 01224030013552 for "repair of Automatic Twist Locks at Wagon Care Centre Tuglakabad for two years"
Rs 2223859.80 (Rupees Twenty Two lakh Twenty Three Thousand Eight Hundred Fifty Nine and Eighty Paise only)
M/S SHREE JAINA SOURCING AND CO- DELHI R 47/D, Dilshad Garden, Delhi - 110095
Work was started on 19-20 Mar-20, thereafter lockdown, work resumed on 18 May 20, Work start date intimated to Division.
[6 empty] | 2223859.8 | 1920
S. No | Bill No & Dt | Month | Bill raised by Firm (in Rs) Excluding GST | Penalty (in Rs) | Bill verified (in Rs) | Balance (in Rs) Excluding GST | ATL repaired | Balance ATL for repair | Torsion Spring replaced | Balance ATL torsion Spring | Groove Pin replaced | Balance Groove Pin
[7 empty] | 48 | 1872
[7 empty] | 197 | 1675
[7 empty] | 216 | 1459
Contract Agreement No. 197-S/86/ATL-Rep/TKD/17/MC-IV dated 14 Jul 2017 Tender for " Repair of Automatic Twist Lock
at Wagon Care Centre, Tuglakabaad over Delhi division for one year
Total cost of contract :--- (Rupees Forty Nine Lakh Five Thousand Five Hundred Eighty Eight only)
M/S Sanrok Enterprises FF-11 Sco-35 Distt: Shopping Centre Sec-16 Faridabad, Haryana
|  |  | Originally awarded----- |  |  | 4905588 |  | 1200 |  | 1100 |  | 100
|  |  | Extension --- |  |  | 1225157 |  | 300 |  | 275 |  | 0
S. No | Bill No & Dt | Month | Bill raised by Firm (in Rs) Excluding GST | Penalty (in Rs) | Bill verified (in Rs) | Balance (in Rs) Excluding GST | ATL repaired | Balance ATL for repair | Torsion Spring replaced | Balance ATL torsion Spring | Groove Pin replaced | Balance Groove Pin
|  | 2016-05-01 |  |  |  |  | 174
|  | 2016-06-01 |  |  |  |  | 224
|  | 2016-07-01 |  |  |  |  | 167
|  | 2016-08-01 |  |  |  |  | 171
|  | 2016-09-01 |  |  |  |  | 162
|  | 2016-10-01 |  |  |  |  | 193
|  | 2016-11-01 |  |  |  |  | 152
|  | 2016-12-01 |  |  |  |  | 139
|  | 2017-01-01 |  |  |  |  | 134
|  | 2017-02-01 |  |  |  |  | 49
|  | 2017-03-01 |  |  |  |  | 8
|  | 2017-04-01 |  |  |  |  | 15
|  | 2017-05-01 |  |  |  |  | 0
|  | 2017-06-01 |  |  |  |  | 0
|  | 2017-07-01 |  |  |  |  | 0
[6 empty] | 6130745 |  | 1500 |  | 1375 |  | 100
1 | SE/RC-VII/001 dated 18/12/2017 | 2017-08-01 | 340954 | 0 | 340954 | 5789791 | 29 | 1471 | 29 | 1346 | 0 | 100
2 | SE/RC-VII/002 dated 18/12/2017 | 2017-09-01 | 800708 | 0 | 800708 | 4989083 | 149 | 1322 | 149 | 1197 | 0 | 100
3 | SE/RC-VII/003 dated 18/12/2017 | 2017-10-01 | 101828 | 0 | 101828 | 4887255 | 78 | 1244 | 65 | 1132 | 0 | 100
4 | SE/RC-VII/004 dated 25/01/2018 | 2017-11-01 | 429727 | 0 | 429727 | 4457528 | 97 | 1147 | 94 | 1038 | 0 | 100
5 | SE/RC-VII/005 dated 25/01/2018 | 2017-12-01 | 36554 | 0 | 36554 | 4420974 | 28 | 1119 | 28 | 1010 | 0 | 100
6 | SE/RC-VII/006 dated 19/02/2018 | 2018-01-01 | 421894 | 0 | 421894 | 3999080 | 91 | 1028 | 86 | 924 | 0 | 100
7 | SE/RC-VII/007 dated 08/03/2018 | 2018-02-01 | 431033 | 0 | 431033 | 3568047 | 98 | 930 | 80 | 844 | 0 | 100
8 | SE/RC-VII/008 dated 05/04/2018 | 2018-03-01 | 380119 | 0 | 380119 | 3187928 | 59 | 871 | 51 | 793 | 0 | 100
9 | SE/RC-VII/009 dated 18/05/2018 | 2018-04-01 | 49609 | 0 | 49609 | 3138319 | 38 | 833 | 31 | 762 | 0 | 100
10 | SE/RC-VII/010 dated 03/07/2018 | 2018-05-01 | 86162 | 0 | 86162 | 3052157 | 66 | 767 | 64 | 698 | 0 | 100
11 | SE/RC-VII/011 dated 03/07/2018 | 2018-06-01 | 369675 | 0 | 369675 | 2682482 | 51 | 716 | 50 | 648 | 0 | 100
12 | SE/RC-VII/012 dated 06/08/2018 | 2018-07-01 | 461059 | 0 | 461059 | 2221423 | 121 | 595 | 117 | 531 | 0 | 100
13 | SE/RC-VII/013 dated 06/08/2018 | 2018-08-01 | 450615 | 0 | 450615 | 1770808 | 113 | 482 | 106 | 425 | 0 | 100
14 | SE/RC-VII/014 dated 24/10/2018 | 2018-09-01 | 374897 | 0 | 374897 | 1395911 | 55 | 427 | 50 | 375 | 0 | 100 | 1560
15 | SE/RC-VII/015 dated 07/12/2018 | 2018-10-01 | 75718 | 0 | 75718 | 1320193 | 58 | 369 | 58 | 317 | 0 | 100
16 | SE/RC-VII/016 dated 07/12/2018 | 2018-11-01 | 90079 | 0 | 90079 | 1230114 | 69 | 300 | 42 | 275 | 0 | 100
17 | SE/RC-VII/017 dated 22/01/2019 | 2018-12-01 | 199851 | 0 | 199851 | 1030263 | 37 | 263 | 37 | 238 | 0 | 100
18 | SE/RC-VII/018 dated 03/04/2019 | 2019-01-01 | 787709 | 0 | 787709 | 242554 | 81 | 182 | 68 | 170 | 0 | 100
19 | SE/RC-VII/019 dated 03/04/2019 | 2019-02-01 | 92690 | 0 | 92690 | 149864 | 71 | 111 | 59 | 111 | 0 | 100
20 | SE/RC-VII/020 dated 03/04/2019 | 2019-03-01 | 120105 | 0 | 120105 | 29759 | 92 | 19 | 92 | 19 | 0 | 100
21 | SE/RC-VII/013 dated 06/08/2019 | 2019-04-01 | 24804 | 0 | 24804 | 4955 | 19 | 0 | 19 | 0 |  | 100
|  | 2019-05-01 |  |  |  |  | 0
|  | 2019-06-01 |  |  |  |  | 0
|  | 2019-07-01 |  |  |  |  | 0
|  | 2019-08-01 |  |  |  |  | 0
|  | 2019-09-01 |  |  |  |  | 0
|  | 2019-10-01 |  |  |  |  | 0
| WORK ORDER | 2019-11-01 |  |  |  |  | 89
|  | 2019-12-01 |  |  |  |  | 189
|  | 2019-01-01 |  |  |  |  | 22
[5 empty] | 6125790 | 4955
6130745

## CAMC of RO
Contract Agreement No. 197-S/183/CAMC-RO/C&W/DLI/17/MC-IV dated 18 May 2018 for “CAMC of RO plant
at different C&W depots (New Delhi, Anand Vihar, Tuglakabad & Ghaziabad) over Delhi division (for 02 years).
Total division contract rate Rs 2839006.00( Rupees Twenty Eight Lakh Thirty Nine Thousand Six only)
M/S ICON RO Systems 3/102-A, Lalita Park, Vikas Marg, Laxmi Nagar, Delhi-92
W.E.F : 27 Jun 2018
S. No | Bill No & Dt FOR THE MONTH | Bill raised by Firm (in Rs)(incl GST) | Penalty (in Rs) | GST @ 18% | Net verified Amount | Bill Amount for PV (in Rs)(excluding GST & Penalty)
|  | A | B | C |  | A- (B+C)
1 | Bill No 302 dtd. 16/12/2019, for Jul 2018 to Sep 2018 | 15668 | 0 | 2390 | 13278 | 13278
2 | Bill No 303 dtd. 16/12/2019, for Oct 2018 to Dec 2018 | 15668 | 0 | 2390 | 13278 | 13278
3 | Bill No 304 dtd. 12/04/2019, for Jan 2019 to Mar 2019 | 15668 | 0 | 2390 | 13278 | 13278
4 | Bill No 111 dtd. 02/07/2019, for Apr 2019 to Jun 2019 | 15668 | 0 | 2390 | 13278 | 13278
5 | Bill No 122 dtd. 14/11/2019, for Jul 2019 to Sep 2019 | 15668 | 0 | 2390 | 13278 | 13278
6 | Bill No 142 dtd. 20/03/2020, for Oct 2019 to Dec 2019 | 15668 | 0 | 2390 | 13278 | 13278
7 | Bill No 150 dtd. 11/05/2020, for Jan 2020 to Mar 2020 | 15668 | 0 | 2390 | 13278 | 13278
8 | Bill No 071 dtd. 23/07/2020, for Apr 2020 to Jun 2020 |  |  |  |  | 0
9
10
11
12
13
14
Completed
Enclosure to ADME/Fr/TKD L.No.197-S/183/CAMC RO/DLI/15-17/MC-IV dtd 04/03/2020
STATUS REPORT " CAMC OF WATER PURIFIERS AND REVERSE OSMOSIS (RO) SYSTEM AT WCC/TKD under
Contract Agreement No. 197-S/183/CAMC-RO/C&W/DLI/15-17/MC-IV dated 11 Dec 2015 for “CAMC of RO plant at different C&W depots
(New Delhi, Anand Vihar, Tuglakabad & Ghaziabad) over Delhi division (for 02 years).
Ref: Control message No. 363 dtd 19/02/2020
|  | 1st quarter 19/04/2016 to 18/07/2016 | 2 nd quarter 19/07/2016 to 18/10/2016 | 3 rd quarter 19/10/2016 to 18/01/2017 | 4 th quarter 19/01/2017 to 18/04/2017 | 5 th quarter 19/04/2017 to 18/07/2017 | 6 th quarter 19/07/2016 to 18/10/2017 | 7 th quarter 19/10/2017 to 18/01/2018 | 8 th quarter 19/01/2018 to 18/04/2018 | 9th extended quarter 19/04/2018 to 18/07/2018 | Remarks | Unit rate (Rs) | % of work attended
SL NO. | M/C description
1 | 200LPH | NA | NA | NA | NA | NA | NA | NA | NA | NA | Declared beyond economical repair by firm | 306 | NIL
2 | 100LPH | Attended | Attended | Attended | Attended | Attended | NA | Attended | Attended | Attended |  | 5625 | 89
3 | 50 LPH | Attended | Attended | Attended | Attended | NA | Attended | Attended | NA | Attended |  | 2500 | 78
| (Bill Claimed) | YES | YES | YES | YES | NO | NO | NO | NO | NO
* Note: Amount was claimed only for the attended job, by the firm in all 4 quarters bill.
Beside above Non-functioning period of RO system during the contract period from 19/04/2016 to 18/07/2018 is as follows:
| R/O | TIME PERIOD |  |  | TOTAL DAYS |  |  | TOTAL DAYS - GRACE PERIOD (48 HRS)
| 100LPH | 12/02/2018 TO 18/03/2018 |  |  | 35 DAYS |  |  | 33 DAYS
| 100 LPH | 10/04/2018 TO 06/05/2018 |  |  | 27 DAYS |  |  | 25 DAYS
| 100 LPH | 21/05/2018 TO 01/06/2018 |  |  | 12 DAYS |  |  | 10 DAYS
[6 empty] | TOTAL |  | 68 DAYS
* AS PER PARA 16 (PENALTY CLAUSE) OF THE CONTRACT RS 500 PER DAY WILL BE CHARGED AGAINST THE NON-ATTENDING DAYS
TOTAL PENALTY : RS 500 X 68 DAYS = RS 34000.00

## CAMC of wheel lathe
Contract Agreement No. 197-S-176-CAMC-Wheel lathe/01279570005082 dated 16/08/19 Tender for
Comprehensive Annual Maintenance Contract of Surface Wheel Lathe (Make-HYT) of wagon care centre, Tuglakabaad. (for 02 Years)
Total division contract rate Rs 2774419.00 (Rupees Twenty Four Lakh Thirt One Thousand Six Hundred Eighty Three and Eight Nine Paise)
M/S SBS Mechanical & Electrical Engineering Works, Military Road, Shiv Mandir P.O New Rangia (N.B.U) Distt-Darjeeling, West Bengal – 734013
W.E.F : 27 Sep 2019
S. No | Bill No & Dt FOR THE MONTH | Bill raised by Firm (in Rs)(incl GST) | Penalty (in Rs) | GST @ 5% | Net verified Amount | Bill Amount for PV (in Rs)(excluding GST & Penalty)
|  | A | B | C |  | A- (B+C)
1
2
3
4
5
6
7
8
9
10
11
12
13
14
Completed
(AMC of comprehensive annual maintenance contract for Two years of surface wheel lathe (make – HYT) of wagon care centre, TKD)
L.O.A. No 197-S-176-AMS-TKD-12-MC-IV Dt 26.09.14
Total Cost of 1st Year comprehensive annual maintenance surface wheel lathe (make – HYT) of wagon care centre, TKD)
|  |  | S. no | Bill No & Dt | Total Cos | Bill raised by Firm | Penalty | Bill Paid | Total Balance
|  |  | 1 | 1st Qtr Bill SBS/00/14 Dt 10.4.14 | 1968000/- | 492000/- | 142500/- | 349500/- | 1476000/-
|  |  | 2 | 2nd Qtr Bill SBS/25/15 Dt 24.9.15 | - | 492000/- | 1205/- | 490795/- | 984000/-
|  |  | 3 | 3rd Qtr Bill SBS/D/02/16 Dt 22.2.16 | - | 492000/- | - | 492000/- | 492000/-
|  |  | 4 | 4th Qtr Bill SBS/18/16 Dt 03.4.16 | - | 492000/- | 4132.8 | 487867.2 | Nil
5

## Housekeeping
Contract Agreement No. 197-S-60-HK-TKD-2017-19-MC-IV dated 17 Nov 2017
regarding mechanized cleaning of floor, pits & toilets, desilting of man holes, drains, disposal
|  | of industrial waste, scrap loading, horticultural, shed & office housekeeping at Wagon Care Centre, Tughlakabad. | [5 empty] | 6046207 | Initial awarded amount in 2017
|  | Total cost of contract :--- (Rupees Sixty Lakh Forty Six Thousand Two Hundred Seven ) | [5 empty] | 1511551.79 | Ist 25 % Extension Amount on 22.11.19
|  | M/S National Enterprises 496, GH-9, Paschim Vihaar Delhi | [5 empty] | 1469218.97 | Iind 25% Extension Amount on 24.05.2020
[8 empty] | 9026977.76 | Total Awarded value
S. No | Month | Bill No./Dated | Bill Raised (excl-GST) (in Rs) | Bill Raised (Incl-GST) (in Rs) | Excess Bill (in Rs) | Total Penalty (in Rs) | Bill Paid (in Rs) | Balance (excl-GST) (in Rs)
1 | 2017-11-01 | 1-NE/17-18/006 dated 31/01/2018 | 44674.98 | 52716.48 | 5817 | 0 | 38858 | 8982302.78 |  | 0
2 | 2017-12-01 | 2-NE/17-18/007 dated 31/01/2018 | 252708.47 | 298195.99 | 5456 | 1441 | 245811 | 8729594.31 |  | 0.57022
3 | 2018-01-01 | 3-NE/17-18/008 dated 31/01/2018 | 232942.97 | 274872.7 | 4308 | 1992 | 226643 | 8496651.34 |  | 0.85514
4 | 2018-02-01 | 4-NE/17-18/00 dated 15/03/2018 | 220867.26 | 260623.36 | 2628 | 14854 | 203385 | 8275784.08 |  | 6.7253
5 | 2018-03-01 | 5-NE/17-18/006 dated 27/04/2018 | 238125.18 | 280987.71 | 482 | 12539 | 225104 | 8037658.9 |  | 5.2657
6 | 2018-04-01 | 6-NE/17-18/006 dated 05/05/2018 | 227217.82 | 268117.02 | 1704 | 13570 | 211944 | 7810441.08 |  | 5.9722
7 | 2018-05-01 | 7-NE/17-18/006 dated 26/07/2018 | 236221.73 | 278741.64 | 9521 | 11798 | 214902 | 7574219.35 |  | 4.9945
8 | 2018-06-01 | 8-NE/17-18/006 dated 26/07/2018 | 201411.98 | 237666.13 | 1727 | 12413 | 187272 | 7372807.37 |  | 6.163
9 | 2018-07-01 | 9-NE/17-18/006 dated 06/08/2018 | 240907.04 | 284270.3 | 3615 | 10521 | 226771 | 7131900.33 |  | 4.3672
10 | 2018-08-01 | 10-NE/17-18/006 dated 06/09/2018 | 212621.28 | 250893.11 | 1976 | 15387 | 195258 | 6919279.05 |  | 7.2368
11 | 2018-09-01 | 11-NE/19-20/017 dated 04/06/2019 | 194246.6 | 229210.99 | 1672 | 22432 | 170143 | 6725032.45 |  | 11.5482
12 | 2018-10-01 | 12-NE/17-18/00 dated 04/06/2019 | 216690 | 255694.9 | 164.472 | 24329 | 192197 | 6508342.45 |  | 11.2276
13 | 2018-11-01 | 13-NE/19-20/019 dated 04/06/2019 | 208717.62 | 246286.79 | 158.63 | 24445 | 184114 | 6299624.83 |  | 11.712
14 | 2018-12-01 | 14-NE/19-20/020 dated 04/06/2019 | 202098.76 | 238476.53 | 4105.04 | 23792 | 174202 | 6097526.07 |  | 11.7725
15 | 2019-01-01 | 15-NE/19-20/021 dated 04/06/2019 | 231627.61 | 273320.57 | 3100.15 | 21866 | 206661 | 5865898.46 |  | 9.4402
16 | 2019-02-01 | 11-NE/19-20/031 dated 24/07/2021 | 206710.97 | 243918.94 | 2538.5 | 29901 | 174271 | 5659187.49 |  | 14.4651
17 | 2019-03-01 | 87 dated 10/01/2020 | 249458.01 | 294360.45 | 2000.84 | 25490 | 221967 | 5409729.48 |  | 10.2182
18 | 2019-04-01 | 88 dated 10/01/2020 | 201583.42 | 237868.43 | 1879.3 | 20025 | 179679 | 5208146.06 |  | 9.9339
19 | 2019-05-01 | 89 dated 10/01/2020 | 231723.13 | 273433.29 | 1890.69 | 23641 | 206191 | 4976422.93 |  | 10.2023
20 | 2019-06-01 | 90 dated 10/01/2020 | 239020.51 | 282044.2 | 3948.15 | 28275 | 206797 | 4737402.42 |  | 11.8295
21 | 2019-07-01 | 91 dated 10/01/2020 | 214085.73 | 252621.16 | 1914.54 | 21270 | 190901 | 4523316.69 |  | 9.9353
22 | 2019-08-01 | 92 dated 10/01/2020 | 200392.24 | 236462.84 | 2307 | 18790 | 179295 | 4322924.45 |  | 9.3766
23 | 2019-09-01 | 93 dated 10/01/2020 | 184008.35 | 217129.85 | 5112.47 | 23620 | 155276 | 4138916.1 |  | 12.8364
24 | 2019-10-01 | 94 dated 10/01/2020 | 226064 | 266755.52 | 11850 | 37028 | 177186 | 3912852.1 |  | 16.3794
25 | 2019-11-01 | 95 dated 10/01/2020 | 212782.28 | 251083.09 | 901 | 35493 | 176388 | 3700069.82 |  | 16.6804
26 | 2019-12-01 | NE/19-20/013, dated 10 Apr 2020 | 229185.67 | 270439.09 | 4083 | 30919 | 194184 | 3683666.43 |  | 13.4908
27 | 2020-01-01 | NE/19-20/014, dated 10 Apr 2020 | 221233.32 | 261055.31 | 495 | 32064 | 188674 | 3462433.11 |  | 14.4933
28 | 2020-02-01 | NE/19-20/015, dated 10 Apr 2020 | 190143.5 | 224369.33 | 165 | 30676 | 159303 | 3272289.61 |  | 16.1331
29 | 2020-03-01 | NE/19-20/16, dated 10 Apr 2020 | 243627.79 | 287480.79 | 3537 | 29306 | 210785 | 3028661.82 |  | 12.029
30 | 2020-04-01 | NE/19-20/17, dated 04 May 2020 | 207652.35 | 245029.77 | 241 | 4520 | 202891 | 2821009.47 |  | 2.1767
31 | 2020-05-01 | NE/20-21/034, dated 10 Jun 2020 | 199072.1 | 234905.07 | 3674.19 | 26429 | 168969 | 2621937.37 |  | 13.2761
32 | 2020-06-01 | NE/20-21/042, dated 06 Jul 2020 | 202576.5 | 239040.27 | 8513.46 | 29652 | 164411 | 2419360.87 |  | 14.6374
|  |  | 6820399.17 | 8048071.62 | 101485.432 | 658478 | 6060433 |  |  | 6.9533
9.6545
Note on H7: Author: Excluding GST since Firm never submitted GST payment proof

## ROUND THE CLOCK WELDING
LOA vide DME/Chg/NDLS letter No. 197-S/190/Prov. Of weld. activity/F.Depot/DLI/18/MC-IV dated 27/05/2019
Tender for “Provision of Round the clock Welding activities in Freight depots
over Delhi Division for Two Years”
Total cost of contract :--(Rupees Two Crore Fifteen Lakh Forty Seven Thousand Two Hundred Fifty Seven and Sixty Paise only)
M/S Singh Enterprises,Near JJ Nursing Home, GT Road, Alinagar, Mughalsarai,Chandauli - 232101
[7 empty] | 21547257.6 |  |  | JUN | JUL | AUG | SEP | OCT | NOC | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | TOTAL | BALANCE
S. No | Bill No & Dt | BILL WITHOUT GST | Bill raised by Firm (in Rs) | Penalty (in Rs) | EXCESS BILL | Bill Paid (in Rs) | Balance (in Rs)
1 | SE/DL/2019/01 DTD 13/12/2019 for Jun 2019 | 275533 | 325128.65 | 26500 | 0 | 249033 | 21298224.6 | GENSET | 730 | 10 | 31 | 31 | 30 | 31 | 30 | DEC: 31; JAN: 31; FEB: 29; MAR: 31; APR: 30; MAY: 31 | 346 | 384
2 | SE/DL/2019/02 DTD 13/12/2019 for Jul 2019 | 785443 | 926823 | 79500 | 5585 | 700358 | 20597866.6 | CONSUMABLE | 730 | 10 | 31 | 31 | 30 | 31 | 30 | DEC: 31; JAN: 31; FEB: 29; MAR: 31; APR: 30; MAY: 31 | 346 | 384
3 | SE/DL/2019/03 DTD 13/12/2019 for Aug 2019 | 895483 | 1056670 | 14750 | 8023 | 872710 | 19725156.6 | WELDER | 11680 | 125 | 441 | 488 | 459 | 459 | 433 | DEC: 473; JAN: 473; FEB: 372; MAR: 414; APR: 378; MAY: 341 | 4856 | 6824
4 | SE/DL/2019/04 DTD 13/12/2019 for Sep 2019 | 860776 | 1015716 | 15000 | 4643 | 841133 | 18884023.6 | HELPER | 11680 | 137 | 399 | 484 | 477 | 447 | 445 | DEC: 479; JAN: 467; FEB: 371; MAR: 444; APR: 392; MAY: 361 | 4903 | 6777
5 | SE/DL/2019/05 DTD 22/05/2020 for Oct 2019 | 852388 | 1005817.96 | 43000 | 12848 | 796540 | 18087483.6 | UNIFORM | 64 | 32 | 0 | 0 | 0 | 0 | 0 | DEC: 0; JAN: 0; FEB: 0; MAR: 0; APR: 0; MAY: 0 | 32 | 32
6 | SE/DL/2019/06 DTD 22/05/2020 for Nov 2019 | 812470 | 958714 | 56400 | 941.69 | 755128 | 17332355.6
7 | SE/DL/2019/07 DTD 22/05/2020 for Dec 2019 | 880312 | 1038769 | 32600 | 2825 | 844887 | 16487468.6 |  |  | 262 | 840 | 972 | 936 | 906 | 878 | DEC: 952; JAN: 940; FEB: 743; MAR: 858; APR: 770
8 | SE/DL/2019/08 DTD 22/05/2020 for Jan 2020 | 872574 | 1029637 | 32200 | 4372 | 836001 | 15651467.6
9 | SE/DL/2019/08 DTD 22/05/2020 for Feb2020 | 701933 | 828281 | 98200 | 9416 | 594316 | 15057151.6 |  |  |  | 941.69 | 773.88
10 | SE/DL/2019/08 DTD 22/05/2020 for Mar 2020 | 809173 | 954824 | 52570 | 14330 | 742272 | 14314879.6 |  | 2019-06-01 | 125 | 117712.5 | 106021.56 | 137 | 223734.06 | 262
11 | SE/DL/2019/08 DTD 22/05/2020 for Apr 2020 | 720267 | 849916 | 0 | 1547.76 | 718720 | 13596159.6 |  | 2019-07-01 | 441 | 415289.7 | 308778.12 | 399 | 724067.82 | 840
12 | SE/DL/2019/08 DTD 22/05/2020 for May 2020 | 661866 | 781003 | 0 | 941.69 | 660925 | 12935234.6 |  | 2019-08-01 | 488 | 459549.6 | 374557.92 | 484 | 834107.52 | 972
13 | [8 empty] | 2019-09-01 | 459 | 432240.3 | 369140.76 | 477 | 801381.06 | 936
14 | [8 empty] | 2019-10-01 | 459 | 432240.3 | 345924.36 | 447 | 778164.66 | 906
[9 empty] | 2019-11-01 | 433 | 407756.1 | 344376.6 | 445 | 752132.7 | 878
[9 empty] | 2019-12-01 | 473 | 445424.1 | 370688.52 | 479 | 816112.62 | 952
[9 empty] | 2020-01-01 | 473 | 445424.1 | 361401.96 | 467 | 806826.06 | 940
[9 empty] | 2020-02-01 | 372 | 350312.4 | 287109.48 | 371 | 637421.88 | 743
[9 empty] | 2020-03-01 | 414 | 389863.8 | 343602.72 | 444 | 733466.52 | 858
[9 empty] | 2020-04-01 | 378 | 355962.6 | 303360.96 | 392 | 659323.56 | 770
[9 empty] | 2020-05-01 | 341 | 321119.7 | 279370.68 | 361 | 600490.38 | 702

## Bogie Modification
Work Order vide DME/Fr letter No. 116-S/Fabn work in BLC/ROH/WCC/TKD/18/MC-IV dated 31/07/2018 for
Fabrication work in BLC Bogie to enhance the axle load capacity at ROH Depot at wagon Care Centre
-Tuglakabad By- M/S Agrya Associates,R/O, RZ – 4/11, Shop No. 6 G/F,KH No. 189, Durga Park
Palam Colony,South East Delhi,Delhi - 110045 for 585 wagons.(with a DP of 06 month)
585 WAGON
LOA vide DME/Chg/NDLS letter No. 197-S/223/Conversion of BLC wagon/TKD/19/MC-IV dated 09/09/2019
Tender for “Conversion of BLC rakes to 22 T axle load - BLCAM/BLCBM wagons as per drawing during ROH activity at wagon care centre, Tuglakabad for Two Years”
Rs 2042163.90 (Rupees Twenty lakh Forty Two Thousand One Hundred Sixty Three and Ninety Paise only)
M/S Global Enterprises, 442, Subhash Puri, Kanpur Khera, Meerut, UP - 250001
[7 empty] | 2042164 | TOTAL | BALANCE |  |  | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN
S. No | Bill No & Dt | BILL WITHOUT GST | Bill raised by Firm (in Rs) | Penalty (in Rs) | EXCESS BILL | Bill Paid (in Rs) | Balance (in Rs) | wagon/bogie | wagon/bogie
1 | 2019-20/020 dated 27/02/2020 for Dec 2019 | 7941.68 | 9371.18 | 2000 | 0 | 5941.68 | 2036222.32 | 608 | 2092 | Wagon | 2700 | DEC: 10.5; JAN: 79; FEB: 108.5; MAR: 57; APR: 0; MAY: 0; JUN: 62.5; JUL: 124.5; AUG: 166
2 | 2019-20/021 dated 28/02/2020 for Jan 2020 | 59751.65 | 70506.83 | 3800 | 0 | 55951.65 | 1980270.67 | 1216 | 4184 | Bogie | 5400 | DEC: 21; JAN: 158; FEB: 217; MAR: 114; APR: 0; MAY: 0; JUN: 125; JUL: 249; AUG: 332
3 | 2019-20/023 dated 01/03/2020 for Feb 2020 | 82063.98 | 96835.49 | 6800 | 0 | 75263.98 | 1905006.69
4 | 2020-21/09 dated 01/07/2020 for Mar 2020 | 43111.95 | 50872.1 | 500 | 0 | 42611.95 | 1862394.74
5 | 2020-21/10 dated 07/07/2020 for Jun 2020 | 47271.88 | 55780.81 | 0 | 0 | 47271.88 | 1815122.86
6 | 2020-21/13 dated 07/08/2020 for Jul 2020 | 94165.58 | 111115.38 | 0 | 0 | 94165.58 | 1720957.28
7
8
9
10
11
12
13
14

## RA to ATL in BFKHN
LOA vide SRDME/FR/NDLS Letter DELHI DIVISION - MECHANICAL / 197- S-226 Retrofitment of ATL / 01224030013704 for
retrofitment of Automatic Twist Locks (ATL) in BFKHN wagons as per drawing at Wagon Care Centre Tuglakabad for 75 wagons
Total cost of contract :--- Rs 2079962.40 (Rupees Twenty lakh Seventy Nine Thousand Nine Hundred Sixty Two and Forty Paise only)
M/S SHREE JAINA SOURCING AND CO- DELHI R 47/D, Dilshad Garden, Delhi - 110095
Originally awarded-----
Extension ---
S. No | BILL PERIOD | Bill No & Dt | Bill raised by Firm (in Rs) Excluding GST | Penalty (in Rs) | Bill verified (in Rs) | Balance (in Rs) Excluding GST | WAGON repaired | WAGON Balance for repair
[5 empty] | 0 | 0
0

## Hiring Truck
LOA vide SRDME/FR/NDLS letter No. DELHI DIVISION - MECHANICAL / 197- S181-Hiring of Truck/01362910013551 dated 13/01/2020 for "Hiring of full body truck (Carrying capacity-9 Ton) at wagon care centre Tuglakabad for transportation of Railway material between depots over Delhi division and JUDW " for 02 years.
"Hiring of full body truck (Carrying capacity-9 Ton) at wagon care centre Tuglakabad for transportation of Railway material between
depots over Delhi division and JUDW " for 02 years.
Rs 2597872.04 (Rupees Twenty Five lakh Ninety Seven Thousand Eight Hundred Seventy Two and Four Paise only)
M/s R K ROADLINES- GHAZIABAD - J 140 A SECTOR 9 VIJAY NAGAR , GHAZIABAD 201009
|  | Vehicle No..UP14JT6398 |  | 2014500 | 100725 |  |  |  |  | 2384025 | 268800
|  | w.e.f 29.02.2020 |  | 2195200.65 | 109760.0325 |  |  |  |  | 2597872.0425 | 292911.36 |  | 2597872.0425
S. No | Period | Invoice/Bill No. & Dt. | Total estimated value/per month | 8.97 % above estimated value/per month | GST @ 5% | Bill raised by Firm (in Rs) Including GST | Bill raised by Firm (in Rs) Excluding GST | Penalty (in Rs) | Bill Paid (in Rs) | Balance(in Rs) including GST | NGT/ECC Paid | Balance NGT/ECC
1 | 29 Feb 2020 to 28 Mar 2020 | RKRL-20-21-04 DTD 06/07/2020 | 83937.5 | 91466.6938 | 4573.3347 | 96040.0284 | 91466.6938 | 500 | 90966.6938 | 2506405.3487 | 0 | 292911.36
2 | 29 Mar 2020 to 28 Apr 2020 | RKRL-20-21-05 DTD 06/07/2020 | 83937.5 | 91466.6938 | 4573.3347 | 96040.0284 | 91466.6938 | 0 | 91466.6938 | 2414938.655 | 0 | 292911.36
3 | 29 Apr 2020 to 28 May 2020 | RKRL-20-21-06 DTD 06/07/2020 | 83937.5 | 91466.6938 | 4573.3347 | 96040.0284 | 91466.6938 | 0 | 91466.6938 | 2323471.9612 | 0 | 292911.36
4 | 29 May 2020 to 28 Jun 2020 | RKRL-20-21-07 DTD 06/07/2020 | 83937.5 | 91466.6938 | 4573.3347 | 96040.0284 | 91466.6938 | 0 | 91466.6938 | 2232005.2675 | 0 | 292911.36
5 | 29 Jun 2020 to 28 Jul 2020 | RKRL-20-21-10 DTD 01/08/2020 | 83937.5 | 91466.6938 | 4573.3347 | 96040.0284 | 91466.6938 | 0 | 91466.6938 | 2140538.5737 | 0 | 292911.36
6 | 29 Jul 2020 to 28 Aug 2020 | RKRL-20-21-15 DTD 01/09/2020 | 83937.5 | 91466.6938 | 4573.3347 | 96040.0284 | 91466.6938 | 466 | 91000.6938 | 2025971.88 | 23100 | 269811.36
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
| Total: |  |  | 548800.1625 | 27440.0081 |  |  | 966 | 547834.1625 | 13643331.6862 | 23100
| Balance: |  |  | 1646400.4875 | 82320.0244 | [5 empty] | 269811.36
Completed
Contract Agreement No. 197-S/175-B/Hiring Vehicle/TKD/16/MC-IV dated 13/06/2017 "Hiring of multi utility vehicle
TATA mobile/TATA xenon etc at wagon care centre for two years
Total cost of contract :--- (Rupees Nine Lakh Seventy Two Thousand Six Hundred Ninety Six and one two paise)
| M/S Sunny Malhotra, 52-Pocket - 1, Paschim Puri, New Delhi | [7 empty] | 972696.12
S. No | Period | Bill No. & Dt. | Bill raised by Firm (in Rs) GST extra |  |  |  |  | Penalty (in Rs) | Bill Paid (in Rs) | Balance (in Rs) GST extra
972696.12
1 | Ist quarter 11/07/2017 to 10/10/2017 | Invoice no. 7 dated 26/10/2017 | 120248.64 |  |  |  |  | 0 | 120248.64 | 852447.48
2 | IInd quarter 11/10/2017 to 10/01/2018 | Invoice no. 14 dated 14/01/2018 | 120248.64 |  |  |  |  | 0 | 120248.64 | 732198.84
3 | IIIrd quarter 11/01/2018 to 10/04/2018 | Invoice no. 4 dated 11/04/2018 | 121078.2 |  |  |  |  | 1000 | 120078.2 | 612120.64
4
5
6
7
8

## Hiring MUV
LOA vide SRDME/FR/NDLS letter No. DELHI DIVISION - MECHANICAL / 197- S175-Hiring - Vehicle/1379020013906 dated 18/01/2020
for "Hiring of Multi-utility Vehicle i.e.TATA XENON/ISUZU D-max or equivalent/ Higher version at Wagon Care Centre, Tuglakabad for Two years.
Total cost of contract :--- Rs 1818298.86 (Rupees Eighteen lakh Eighteen Thousand Two Hundred Ninety Eight and Eight Six Paise only)
M/s ARAMISH INDIA PRIVATE LIMITED- NEW DELHI, PLOT NO. 185 FIE. PATPARGANJ INDUSTRIAL AREA, NEW DELHI 110092
|  | Vehicle No..HR26EG0274 |  |  | 33.36 | 33.0931
|  | w.e.f 13.03.2020 |  | 1191836.57 | 8640 | 285924.55 | 1477761.13 | 73888.12 |  |  |  | 1551648.69 | 266649.6 |  |  | 1818298.84
S. No | Period | Bill No. & Dt. | Total estimated value/per month | 0.8 % below estimated value/per month | Extra Hrs | Extra charges for Extra Hrs | Bill raised by Firm (in Rs) Excluding GST | GST @ 5% | Bill raised by Firm (in Rs) Including GST | Penalty (in Rs) | Bill Paid (in Rs) | Balance(in Rs) including GST | NGT/ECC Paid | Balance NGT/ECC Paid | Total Bill raised by Firm (in Rs) Including GST, ECC, Extra hours | Balance Amount (in Rs)
1 | 2020-03-01 | Invoice no. MT-1013 dtd 01/04/2020 | 50060.34 | 30436.67 | 228 | 7545.2314 | 37981.9014 | 1899.0951 | 39880.9964 | 0 | 39880.9964 | 1511767.6936 | 0 | 266649.6 | 39880.9964 | 1778417.8436
2 | 2020-04-01 | Invoice no. MT-1015 dtd 01/05/2020 | 50060.34 | 49659.8573 | 360 | 11913.5232 | 61573.3805 | 3078.669 | 64652.0495 | 0 | 64652.0495 | 1447115.6441 | 0 | 266649.6 | 64652.0495 | 1713765.7941
3 | 2020-05-01 | Invoice no. MT-1016 dtd 01/06/2020 | 50060.34 | 49659.8573 | 360 | 11913.5232 | 61573.3805 | 3078.669 | 64652.0495 | 0 | 64652.0495 | 1382463.5946 | 0 | 266649.6 | 64652.0495 | 1649113.7446
4 | 2020-06-01 | Invoice no. MT-1018 dtd 30/06/2020 | 50060.34 | 49659.8573 | 360 | 11913.5232 | 61573.3805 | 3078.669 | 64652.0495 | 0 | 64652.0495 | 1317811.5451 | 0 | 266649.6 | 64652.0495 | 1584461.6951
5 | 2020-07-01 | Invoice no. MT-1018 dtd 30/06/2020 | 50060.34 | 49659.8573 | 360 | 11913.5232 | 61573.3805 | 3078.669 | 64652.0495 | 0 | 64652.0495 | 1253159.4956 | 0 | 266649.6 | 64652.0495 | 1519809.6456
6 | 2020-08-01 | Invoice no. MT-1018 dtd 30/06/2020 | 50060.34 | 49659.8573 | 360 | 11913.5232 | 61573.3805 | 3078.669 | 64652.0495 | 0 | 64652.0495 | 1188507.4461 | 0 | 266649.6 | 64652.0495 | 1455157.5961
7 | 2020-09-01
8 | 2020-10-01
9 | 2020-11-01
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
| Total: |  |  | 179416.2418 | 1308 | 43285.801 | 222702.0428 | 11135.1021 | 233837.1449 | 0 | 233837.1449
| Balance: |  |  | 1012420.3282 | 7332 | 242638.749 | 1255059.0872 | 62753.0179
Completed
Contract Agreement No. 197-S/175-B/Hiring Vehicle/TKD/16/MC-IV dated 13/06/2017 "Hiring of multi utility vehicle
TATA mobile/TATA xenon etc at wagon care centre for two years
Total cost of contract :--- (Rupees Nine Lakh Seventy Two Thousand Six Hundred Ninety Six and one two paise)
| M/S Sunny Malhotra, 52-Pocket - 1, Paschim Puri, New Delhi | [9 empty] | 972696.12
S. No | Period | Bill No. & Dt. | Bill raised by Firm (in Rs) GST extra | [6 empty] | Penalty (in Rs) | Bill Paid (in Rs) | Balance (in Rs) GST extra
972696.12
1 | Ist quarter 11/07/2017 to 10/10/2017 | Invoice no. 7 dated 26/10/2017 | 120248.64 | [6 empty] | 0 | 120248.64 | 852447.48
2 | IInd quarter 11/10/2017 to 10/01/2018 | Invoice no. 14 dated 14/01/2018 | 120248.64 | [6 empty] | 0 | 120248.64 | 732198.84
3 | IIIrd quarter 11/01/2018 to 10/04/2018 | Invoice no. 4 dated 11/04/2018 | 121078.2 | [6 empty] | 1000 | 120078.2 | 612120.64
4
5
6
7
8
Note on F7: Author: Estimated Price
Note on G7: Author: Accepted price .8% down to estimated price…..
Note on B10: Author: 13 Mar 2020 to 31 Mar 2020 = 19 Days Estimated value for month i.e 31 days = 50060.34 Accepted Value .8% down = 49659.85 per day value =49659.85/31 = 1601.93 Value for 19 days = 19 X 1601.93 =30436.67
Note on E10: Author: for 19 Days

## CAMC OF OH CRANE
LOA vide SRDME/FR/NDLS letter No. DELHI DIVISION - MECHANICAL / 197- S187 CAMC of OH Cra/00919360014303 dated 24/01/2020 for
Comprehensive Annual Maintenance Contract for Over Head Cranes at Wagon Care Centre, Tughlakabad.
Total division contract rate Rs 4041924.05 (Rupees Forty lakh Fourty One Thousand Nine Hundred Twenty Four and Zero Five Paise only)
M/s JAY TECHNICAL SERVICES - KOLKATA, 26/1/1B STRAND ROAD 4TH FLOOR ROOM NO.4 KOLKATA -700001, WEST BENGAL INDIA
W.E.F : 24 May 2020
S. No | Bill No & Dt FOR THE QUARTER | Bill raised by Firm (in Rs)(incl GST) | Penalty (in Rs) | GST @ 5% | Net verified Amount | Bill Amount for PV (in Rs)(excluding GST & Penalty)
|  | A | B | C |  | A- (B+C)
1
2
3
4
5
6
7
8
9
10
11
12
13
14